**WCPFC Intersessional Working Group on the Review of the Compliance Monitoring Scheme (CMS IWG)**

**Work Plan**

**24 April 2018[[1]](#footnote-1)**

This paper: (a) the scope of the task from WCPFC14, (b) establishes a plan for completing the work, and (c) lists the group’s participants.

1. **Scope**

As agreed at WCPFC14 the tasks of the IWG will be to facilitate consideration of the Report from the Independent Review of the CMS and develop a proposed Conservation and Management Measure for the Compliance Monitoring Scheme for consideration at WCPFC15. (refer to WCPFC14 Report paragraph 461)

1. **Workplan**

|  |  |
| --- | --- |
| 1. Issue Final Report from Panel to review the CMS (Circ. 2018-15) | 7 March 2018 |
| 1. Commence CMS IWG (Circ. 2018-16) | 9 March 2018 |
| 1. Request initial comments on Panel’s Report on review of CMS, and in view of task to develop proposed CMM for CMS (Circ. 2018-16) | 30 March 2018 |
| 1. Secretariat creates CMS IWG reference webpage https://www.wcpfc.int/cms-iwg | 9 April 2018 |
| 1. Development of draft workplan (via email) | April 2018 |
| 1. Development of draft consultative proposed CMM for CMS (via email) | April – August 2018 |
| 1. Consideration of draft proposed CMM for CMS (at TCC14) | 26 Sept – 2 Oct 2018 |
| 1. Further discuss Final Report from Review Panel (at TCC14) | 26 Sept – 2 Oct 2018 |
| 1. Finalize draft proposed CMM for consideration at WCPFC15 | 9 November 2018 |
| 1. Commission to consider proposed CMM for CMS as prepared by CMS IWG (at WCPFC15). The Final Report from Panel to Review the CMS will also be considered. | 3 – 7 December 2018 |

1. **CMS IWG participants** (*nominated in response to Circular 2018-16 as at 20 June 2018*)

| **Delegation** | **Name** | **Email contact** |
| --- | --- | --- |
| Republic of Marshall Islands | Glen JOSEPH (**Chair**) | gjoseph@mimra.com |
| Australia | Jenny BALDWIN | jenny.baldwin@agriculture.gov.au |
| Australia | Mat KERTESZ | mat.kertesz@agriculture.gov.au |
| Canada | Christopher (Chris) FRENCH | christopher.french@dfo-mpo.gc.ca |
| European Union | Angela MARTINI | Angela.MARTINI@ec.europa.eu |
| European Union | Stamatios Varsamos | Stamatios.Varsamos@ec.europa.eu |
| Japan | Wataru TANOUE | wataru\_tanoe630@maff.go.jp |
| Japan | Takahiro FUJIWARA | takahiro\_fujiwara550@maff.go.jp |
| Republic of Korea | Seunglyong (Leon) KIM | kpoksl5686@korea.kr |
| Republic of Korea | Minjeong CHO | jasmin1210@korea.kr |
| Republic of Marshall Islands | Sam LANWI | skljr@mimra.com |
| Republic of Marshall Islands | Laurence EDWARDS | ledwards@mimra.com |
| New Zealand | Megan LINWOOD | megan.Linwood@mpi.govt.nz |
| New Zealand | Joanne DOW | joanne.dow@mfat.govt.nz |
| Papua New Guinea | Joseph KENDOU | jkendou@fisheries.gov.pg |
| Chinese Taipei | Shirley, Shih-Ning Liu | shirley@ofdc.org.tw |
| Chinese Taipei | Joy, Hsiang-Yi Yu | hsiangyi@ms1.fa.gov.tw |
| Tonga | Poasi NGALUAFE | poasif@tongafish.gov.to |
| United States of America | Tom GRAHAM | tom.graham@noaa.gov |
| United States of America | Emily CRIGLER | emily.crigler@noaa.gov |
| FFA Secretariat | Manu TUPOU-ROOSEN | manu.tupou-roosen@ffa.int |
| FFA Secretariat | Pamela MARU | pamela.maru@ffa.int |
| FFA Secretariat | Viv FERNANDES | vivian.fernandes@ffa.int |
| PNA Office representative | Wez NORRIS | wez.norris@pontus.com.au |
| TCC Chair | Alexa COLE | Alexa.cole@noaa.gov |
| Secretariat | Feleti TEO | Feleti.teo@wcpfc.int |
| Secretariat | Penny RIDINGS | pennyridings@yahoo.com |
| Secretariat | Lara MANARANGI-TROTT | lara.manarangi-trott@wcpfc.int |
| Secretariat | ‘Ana TAHOLO | ana.taholo@wcpfc.int |
| SPC-OFP(Scientific Services Provider) | Peter WILLIAMS | peterw@spc.int |
| International Seafood Sustainability Foundation | Holly KOEHLER | hkoehler@iss-foundation.org |
| Claire VAN DER GEEST | cvandergeest@iss-foundation.org |
| The Pew Charitable Trusts | Dave GERSHMAN | dgershman@pewtrusts.org |
| Birdlife | Karen BAIRD | k.baird@forestandbird.org.nz |

--

1. Updated 5 and 20 June 2018, to include additional IWG participants [↑](#footnote-ref-1)